## Sheet1
Project Title: | Hangman Game |  |  | Start Date: March 4th, 2020
Programmer's Name: | Ishav Sohal |  |  | End Date: March 23rd, 2020
Date: | March 9th, 2020
All Time Estimates | * Beginning of Day * | * Beginning of Day * | * One Work Day = 3 Hours of work *
Sub Task | Start Time (Day #) | End Time (Day #) | Length of Task (In "Work Days") | Progress %
Scope Document | 1 | 3 | 2 | 100
Feasibility Study | 3 | 5 | 2 | 100
Introduction Screen | 5 | 5 & 1/3 | 2020-01-03 | 100
Win/Lose Screens | 5 & 1/3 | 5 & 2/3 | 2020-01-03 | 100
Game Screen | 5 & 2/3 | 6 | 2020-01-03 | 100
Main Game | 6 | 11 | 5 | 100
Encapsulation | 11 | 12 | 1 | 100
User Guide | 12 | 14 | 2 | 100
Testing | 14 | 15 | 1 | 100
Reflection Report | 15 | 16 | 2 | 100
Total Time | 1 | 17 | 16 work days (or 48 hours) | 100
(This is for the graph on the right)
|  | Sub Tasks | Length of Task (In "Work Days")
|  | Scope Document | 2
|  | Feasibility Study | 2
|  | Introduction Screen | 0.33333
|  | Win/Lose Screen | 0.33333
|  | Game Screen | 0.33333
|  | Game | 5
|  | Encapsulation | 1
|  | User Guide | 2
|  | Testing | 1
|  | Reflection Report | 2
|  | Total Time | 16 work days (or 48 hours)